## Example
Enter information in highlighted rows (example already entered). Red and purple on chart highlight late execution according to plan.
|  | Planned |  | Actual |  | 2010-04-01 |  | 1st bar | 2nd bar |  |  |  | 4th bar | 3rd bar
Item # | Activity | Start Date | Stop Date | Start Date | Stop Date | plan start | actual start | start | delay | plan stop | actual stop | stop | end delay | delta
1 | Research | 2010-04-01 | 2010-04-15 | 2010-04-02 | 2010-04-16 | 0 | 1 | 0 | 1 | 14 | 15 | 14 | 1 | 13
2 | Plan | 2010-04-15 | 2010-04-30 | 2010-04-14 | 2010-04-29 | 14 | 13 | 13 | 0 | 29 | 28 | 28 | 0 | 15
3 | build | 2010-04-30 | 2010-05-15 | 2010-04-30 | 2010-05-15 | 29 | 29 | 29 | 0 | 44 | 44 | 44 | 0 | 15
4 | expt | 2010-05-15 | 2010-05-30 | 2010-05-15 | 2010-05-30 | 44 | 44 | 44 | 0 | 59 | 59 | 59 | 0 | 15
5 | write | 2010-05-30 | 2010-06-15 | 2010-05-30 |  | 59 | 59 | 59 | 0 | 75 |  | 75 |  | 16
6 | Present | 2010-06-15 |  |  |  | 75 |  | 75 | [5 empty] | 1
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Instructions
Some knowledge of Excel is required to use this spreadsheet, however unless your project is greater than 9 rows the knowledge required is minimal.
Formulas for 100 rows are entered. If you have a more complex project I would recommend purchasing project planning software rather than continue to attempt to use this Excel spreadsheet.
It is possible to copy and paste to make more rows, but more extensive experience with Excel is needed.
Only a few rows (9) are displayed on the chart. To display more it is necessary to edit the data selected to add rows.
Right click on the chart and choose "select data"
Select each data series (including horizontal) and click "edit".
In the box labeled "Series values:" (Horizontal: "Axis label range:") change the row from 12 to the last row number you are using or larger row number.
Note this Excel spreadsheet does NOT provided for error checking dates. If one activity requires completion of another, it is possible to enter a start date prior to completion of the required activity.
The intent of this spreadsheet is simple project planning, not a comprehensive software package. Something a student might use to organize a simple project.
Best Regards,
Jim Sizemore, Ph.D.
Professor of Physics
Collin College